Stackly Website Builder Application

Project overview: setup, structure and sprint delivery plan

Prepared: 11 July 2026

# 1. Executive summary

Stackly is a no-code website builder. A user can create a project, choose a template, assemble a page with visual blocks, preview it at different device sizes, save it, and export the generated site.

The codebase is a monorepo with a Next.js frontend and an Express/MongoDB backend. Work is organised into eleven product modules delivered across six sprints so that progress can be planned, built and verified in clear functional slices.

Current position: the core customer journey is implemented. The builder, project workspace, templates, preview and blog capabilities are usable. Remaining work is concentrated in production publishing, domains, e-commerce UI, analytics integration and AI assistance.

# 2. Project setup and structure

## Repository layout

Website-Builder-Application/

•  frontend/ — Next.js 16, React 19, TypeScript and Tailwind v4. Contains user pages, the visual builder, reusable components, Zustand stores and API clients.

•  backend/ — Node.js, Express and MongoDB. The active API structure, organised into routes, controllers, services, models, validators and middleware.

•  docs/ — delivery dashboard, technical planning material and this project overview.

•  .github/workflows/ — GitHub Actions workflow for automated deployment.

## How deployment works (Static export → GitHub Pages)

The frontend is configured with output: "export" in next.config.mjs. This means Next.js generates a fully static site (plain HTML, CSS, JS) at build time — no Node.js server is needed to host the frontend.

Why static export matters:

•  The entire frontend compiles into an out/ folder of static files.

•  These files can be hosted on any static file server — in our case, GitHub Pages.

•  Images are set to unoptimized: true because GitHub Pages cannot run Next.js image optimisation on the server side.

•  A base path (NEXT_PUBLIC_BASE_PATH: /Website-Builder-Application) is injected during build so all asset URLs work correctly under the GitHub Pages sub-path.

## GitHub Actions CI/CD pipeline

A workflow in .github/workflows/deploy.yml automates the entire deployment on every push to main:

•  Checkout code → Install dependencies → Run next build (static export)

•  Add .nojekyll file (tells GitHub Pages not to process files through Jekyll)

•  Copy docs/ into the build output so docs are published alongside the app

•  Upload the out/ folder as a GitHub Pages artifact and deploy it

The frontend deploy script (npm run deploy) also supports manual deployment using the gh-pages package as an alternative.

## Runtime flow

User action → Next.js page/component → Zustand state store → typed API client → Express route → controller → service → MongoDB model.

The builder keeps client-side editing state for fast interaction. It saves project data and generated HTML through the Project API, while UI preferences like canvas grid settings remain local to the browser.

## Local setup

•  Install dependencies separately in backend/ and frontend/ with npm install.

•  Copy each .env.example and provide MongoDB, JWT and optional provider credentials.

•  Start the backend on port 5000 and the frontend on port 3000. The frontend uses NEXT_PUBLIC_API_BASE_URL to reach the API.

# 3. How we work

Each module is a product capability with an explicit user outcome, owning screens, state, API paths and acceptance checks. This keeps delivery understandable without requiring every stakeholder to follow implementation detail.

## Standard workflow

•  Scope the user outcome and identify the affected module(s).

•  Define the data contract and validation rules before wiring the UI.

•  Build the frontend component and state changes in the relevant feature folder.

•  Build or extend the API through route → validator → controller → service → model.

•  Connect the typed API client, handle loading and failure states, and preserve data compatibility.

•  Verify with linting, TypeScript checks and feature-level behaviour checks.

## Definition of done

A task is marked done only when its intended user-facing flow is implemented and checked in the active code path. Partial means code or backend scaffolding exists but is not yet fully exposed or production-ready. Pending means it is intentionally not started.

# 4. Sprint delivery plan

Work is divided into six sprints across two phases. Each sprint lists simple backend and frontend tasks.

| Sprint | Duration | Modules | Priority |
| --- | --- | --- | --- |
| Sprint 1 | 2 Weeks | Authentication & User Management | Critical |
| Sprint 2 | 2 Weeks | Workspace, Dashboard & Templates | Critical |
| Sprint 3 | 3 Weeks | Drag-and-Drop Builder & Preview | Critical |
| Sprint 4 | 2 Weeks | Publishing, Domain & Hosting | High |
| Sprint 5 | 3 Weeks | E-commerce & Blog/SEO | High |
| Sprint 6 | 2 Weeks | Analytics & AI Assistant | Medium |

Phase 1 — Core Platform

Goal: Deliver a fully functional website builder where users can sign up, build pages visually, and publish live sites.

## Sprint 1: Authentication & User Management (2 Weeks)

Secure user registration, login, identity verification and subscription management.

Backend

•  Setup Express app with CORS, rate limiting and error handling

•  Implement JWT authentication (access + refresh tokens)

•  Create user registration and login APIs

•  Build email/mobile OTP verification flow

•  Implement forgot and reset password flow

•  Configure email service (Nodemailer/SMTP)

•  Integrate Google OAuth via Passport.js

•  Create user profile API (get and update)

•  Implement plan-based feature gating middleware

•  Integrate Razorpay/Stripe payment gateway

•  Handle subscription lifecycle (upgrade/downgrade/cancel)

Frontend

•  Build signup and login pages with form validation

•  Build forgot password and password reset pages

•  Build email and mobile verification pages

•  Implement Google OAuth login flow

•  Build profile settings UI

•  Implement Razorpay checkout integration

•  Build plan selection and upgrade UI

•  Implement route protection for authenticated pages

Deliverable: Users can register, log in (email or Google), verify identity, manage profile and subscribe to a plan.

## Sprint 2: Workspace, Dashboard & Templates (2 Weeks)

Project management dashboard and browsable template library.

Backend

•  Create Workspace and WorkspaceState models

•  Build workspace CRUD APIs (create, list, update, delete)

•  Build workspace duplicate and autosave APIs

•  Create Template model with categories and tags

•  Build template listing, detail and clone APIs

•  Build template cart and wishlist APIs

•  Seed 3–5 base templates (Portfolio, Blog, Store)

•  Configure AWS S3 for asset uploads

Frontend

•  Design and build the main dashboard page

•  Build 'Create Project' flow

•  Implement project listing, delete and duplicate

•  Build project settings page

•  Build template library page with category filters

•  Build template preview and 'Use Template' flow

•  Build template cart and wishlist UI

Deliverable: Users can create and manage projects from a dashboard and browse or clone templates to start building.

## Sprint 3: Drag-and-Drop Builder & Preview (3 Weeks)

Core visual editor with 27+ block types, styling controls and responsive preview.

Backend

•  Finalize JSON schema for page structure

•  Build save and load page structure APIs

•  Implement autosave with debounced persistence

•  Build asset upload/listing APIs (images to S3)

Frontend

•  Build the editor canvas UI

•  Implement drag-and-drop system for all block types

•  Create all block components (text, image, video, button, hero, header, footer, form, gallery, testimonial, pricing, FAQ, CTA, map, social, etc.)

•  Build layout system (sections, rows, columns)

•  Build styling controls panel (font, color, spacing, borders)

•  Build component settings panel

•  Implement undo/redo functionality

•  Save and load page structure as JSON

•  Build preview renderer (HTML/CSS output from JSON)

•  Add desktop, tablet and mobile preview modes

•  Implement responsive breakpoints and live preview sync

Deliverable: Users can visually build pages using drag-and-drop, customise styles, preview across devices, with autosave and undo/redo.

## Sprint 4: Publishing, Domain & Hosting (2 Weeks)

Convert built pages to live sites with subdomain and custom domain support.

Backend

•  Build JSON-to-static-HTML conversion engine

•  Generate CSS from design tokens and component styles

•  Bundle assets and deploy to S3

•  Build publish API with deployment status tracking

•  Store deployment versions and implement rollback

•  Generate unique subdomains

•  Build custom domain verification flow (DNS check)

•  Integrate SSL provisioning

Frontend

•  Build 'Publish' button with status indicator (loading/success/fail)

•  Build deployment history and rollback UI

•  Build subdomain and custom domain settings UI

•  Build domain verification status UI

Deliverable: Users can publish sites to a live URL with SSL and roll back to previous versions if needed.

Phase 2 — Extended Features

Goal: Add monetisation (e-commerce), content marketing (blog/SEO), data insights (analytics) and AI-powered tools.

## Sprint 5: E-commerce & Blog/SEO (3 Weeks)

Enable online stores and content-driven sites with SEO optimisation.

Backend

•  Create Product model and build product CRUD APIs

•  Build cart, checkout and order management APIs

•  Integrate payment gateway for product purchases

•  Create BlogPost model with slug and SEO fields

•  Build blog post CRUD APIs

•  Generate sitemap.xml and Open Graph meta tags

Frontend

•  Build product management UI (add/edit/delete)

•  Implement shopping cart and checkout flow

•  Build order management dashboard

•  Build blog editor UI with rich text editing

•  Build blog listing page

•  Build SEO metadata fields and Open Graph preview UI

Deliverable: Users can add an online store to their site and publish SEO-optimised blog content.

## Sprint 6: Analytics & AI Content Assistant (2 Weeks)

Traffic insights and AI-powered content generation tools.

Backend

•  Build page-view tracking script

•  Build analytics tracking and dashboard APIs

•  Integrate AI text generation API (OpenAI/Gemini)

•  Integrate AI image generation API

•  Build layout suggestion API

Frontend

•  Build analytics dashboard with charts and traffic metrics

•  Add Google Analytics integration (optional)

•  Add 'Generate Text' button in the builder editor

•  Build AI image placeholder generator

•  Implement layout suggestion UI based on content type

Deliverable: Users can view site analytics and use AI tools to generate content and images within the builder.

# 5. Current module status

| Module | Status | Notes |
| --- | --- | --- |
| Authentication & Users | Delivered | Registration, login, OTP, Google sign-in working. Refresh token handling and full plan gating are follow-up. |
| Workspace & Dashboard | Delivered | Create, list, duplicate, delete and save projects working. |
| Template Library | Delivered | Browse, preview and clone templates working. Larger curated content is ongoing. |
| Drag-and-Drop Builder | Delivered | 27+ blocks, drag-and-drop, styling, responsive editing, undo/redo, save/export working. |
| Preview & Responsive | Delivered | Desktop, tablet and mobile frames with stored responsive style overrides. |
| Domain & Hosting | Foundation | Models and service scaffolding exist. DNS, SSL and routing are not live. |
| Publishing System | Partial | HTML generation and project save delivered. Deploy status and rollback not yet connected. |
| E-commerce | Foundation | Backend foundations exist. Product, cart and checkout UI still needed. |
| Blog & SEO | Partial | Editor, schema, slugs and sitemap implemented. Frontend API alignment pending. |
| Analytics | Partial | Dashboard UI delivered. Event ingestion and reporting need backend integration. |
| AI Content Assistant | Planned | Not started. Block definitions leave space for future generation features. |

# 6. Next priorities and risks

## Recommended sequence

•  Consolidate backend services and align route names used by frontend API clients.

•  Deliver a publish flow with deployment status, safe failure handling and hosted-site output.

•  Connect analytics ingestion and dashboard reporting to the active backend.

•  Bring e-commerce APIs into the live backend and introduce product, cart and checkout UIs.

•  Add AI assistance only after the core publishing and measurement loops are stable.

## Risks to manage

•  Backend duplication: the repository contains active and reference backend implementations. Consolidation ownership and route compatibility should be agreed before adding more API-dependent features.

•  Infrastructure scope: domain, hosting and deployment require real cloud, DNS and security decisions — these are not just frontend tasks.

•  Data ownership: browser-first editing is appropriate for responsiveness, but project saves must remain authoritative on the backend as collaboration and publishing grow.

# 7. Tech stack reference

| Layer | Technology |
| --- | --- |
| Frontend | Next.js 16 (App Router) + React 19 + TypeScript + Tailwind v4 |
| State Management | Zustand |
| Backend | Node.js + Express.js |
| Database | MongoDB (Mongoose) |
| Authentication | JWT + Google OAuth (Passport.js) |
| Payment | Razorpay (primary) + Stripe (optional) |
| Cloud Storage | AWS S3 |
| Email | Nodemailer (SMTP) |
| Deployment | GitHub Pages (static export) + GitHub Actions CI/CD |
| AI (planned) | OpenAI / Google Gemini APIs |

Total estimated duration: 14 weeks (3.5 months)

Phase 1 (Core Platform): 9 weeks — Sprints 1 through 4

Phase 2 (Extended Features): 5 weeks — Sprints 5 through 6

For the detailed live task list, source paths and status definitions, open docs/index.html in this repository.